Biostatistics Research Support: Annual Activity and Capacity Report

Reporting period: October 9, 2025 – October 9, 2026

Prepared by :  Lomas Persad, Biostatistician 2, Department of Ophthalmology

Date prepared: October 9, 2026

1. Executive summary

30 unique projects with recorded activity during the past 12 months, including previously submitted projects that continued to receive support and pending projects.  There were 17 new submissions during this reporting period. This count includes 4 IRIS projects where I only extracted data/clean the data.

2. Project volume and categories

Table 1. Projects with activity during the reporting period

| Project status | Unique projects | Interpretation |
| --- | --- | --- |
| Completed | 14 | Recorded as completed, with activity or completion during the period |
| Ongoing | 6 | Active projects requiring further support |
| Pending | 9 | Submitted projects not yet initiated, according to the register |
| On hold | 1 | Project temporarily paused |
| Total | 30 | Unique projects with recorded activity |

Table 2. Cosmos/IRIS counts

| Database | Unique projects |
| --- | --- |
| IRIS Registry | 18 |
| COSMOS | 10 |
| Both IRIS and COSMOS | 2 |
| Total | 30 |

Table 3. New submissions during the past 12 months

| Status | Projects submitted |
| --- | --- |
| Completed | 3 |
| Ongoing | 4 |
| On hold | 1 |
| Pending | 9 |
| Total new submissions | 17 |

3. Research output and project support time/delay

Three confirmed publications in the 1 year period

Typical submission-to-start delay: 145 days ( median of 20 projects)

Typical support period: 30 days (median of 13 completed projects with recorded support time)

Average support period: 90 days (Mean of those 13 completed project)

Long-running projects: 150–260+ days (Observed among several completed projects)

4. Resources and future needs

Research output tracking

There is currently no systematic way to capture the downstream output of supported work — abstracts, conference presentations, or peer-reviewed publications.

Workflow automation and infrastructure

Project management has been possible with AI assistance. It was, however, assembled incrementally rather than designed.

I plan to create two automations that would convert recurring manual effort:

- Intake-to-workspace pipeline. An agent reads an incoming project request, extracts the PI, title, database, aims, and required variables, and scaffolds the project workspace and register entry automatically.

- Ambiguity review. An agent reviews each new request against the data dictionary and prior project patterns, and returns a documented list of ambiguities, missing fields, and definitional conflicts before extraction coding begins.

The plan is to use Organization/department resources to host.